**Addendum 5**

**RFP – Solar Services Agreement**

Please note the following information/updates (changes are in red text):

Table 2-5 of Paragraph 2 of the RFP is amended as follows:

|  |
| --- |
| **Table 2-5. Program Milestones** |
| **Milestone** | **Date** |
| Notice of Intent to Award | Week of 12/5/2022 |
| Investment Grade Audit | 12/12/22 |
| Site Due Diligence Complete for All Sites | 2/28/2023 |
| Site Financial Closing (As Applicable per Site) | 5/31/2023 |
| Notice to Proceed Issued For All Projects | 6/1/2023 |
| Mechanical Completion For All Projects | 8/1/2024 |
| Performance Testing Completed | 9/1/2024 |
| Substantial Completion | 10/1/2024 |
| Commercial Operations Achieved for All Projects | 10/31/2024 |

Paragraph 6 of the RFP is amended as follows:

6. PROJECTED TIMETABLE OF ACTIVITIES

The schedule will apply to this RFP but may change in accordance with the UA's needs.

|  |  |
| --- | --- |
| **Table 6-1. Projected Procurement Timetable** |  |
| **Event** | **Date** |
| RFP issued | 9/12/22 |
| Pre-proposal meeting at University of Arkansas System Office or via Zoom – 10:00 a.m. | 9/28/22 |
| Questions due | 9/30/22 |
| Answers posted | 10/7/22 |
| Proposals due | 11/7/22 |
| Interviews beginning | 11/30/22 |
| Notice of Intent to Award (contract conditional on approval by the Board of Trustees) | Week of 12/5/22 |